## Project Charter
<Sample Project Title>
Project Identification |  |  | Strategic Alignment
Application |  |  | Strategic Alignment | Social Responsibility
Exec Resp. / Sponsor |  |  | Supported Priority | SAVE: Increase HR Efficiency/meet cost reduction target/ new budget
Project manager /Resp. |  |  | Customer Value | Strategy, Architecture & Integration
Duration (month) |  |  | CoE Initative | TALENT SOLUTIONS: Engaged employees & leaders in right job at right time
Cost |  |  | Metric/Objective | Metrics |  | Objective | - reduce time to create new record in DB by 25% until end the end of this year - …
Cost Class | 4 - high cost 150k€ - 300k€ |  | Other Metrics Impacted | Data Quality
IT Cost (k€) |  | Funtion Cost (k€)
General Description (Why and What) |  |  | Specific Deliverables (output)
1.) WHY (business case): <enter description why you want to run this initiative> 2.) WHAT: <enter high level description of what you want to do - these are the activities, the deliverables should be entered on the right side> |  |  | 1. Data model alignment between system A and system B 2. Architecture describing the new to-be landscape 3. Implementation of xyz in system A 4. Development of scripts 5. Implementation of interfaces 6. Rollout
In Scope (Inclusions) |  | Known Dependencies With Other Processes |  |  | Major Success Factors (Assumptions)
Out of Scope (Exclusions) |  | IT Scope | Stakeholders |  | Risks / Constraints
Team members |  | Business Value
CORE TEAM: EXTENDED TEAM: IT TEAM: |  | 1. Does it support the ata integrity initiative? |  | 3 - medium improvement |  |  | HR Business Value
|  | 2. Does it increase efficiency / lower cost? |  | 1 - no cost savings |  |  | 69
|  | 3. What is the number of effected employees? |  | 2 - less than 100 employees effected
|  | 4. In how far does it improve system integration? |  | 5 - process seamlessly integrated over different systems
|  | 5. Does it deliver value (e.g. improved business processes)? |  | 2 - little added value
|  | 6. Is it required for governance or to "keep the lights on"? |  | 2 - little impact
Note on C3: martin kramer: Title of the project idea or initiative
Note on C10: martin kramer: Even at a very early stage, the cost is an important driver for any decision about a project. Thus, please provide at least the cost class. If further informtation is available, use the cost-sheet to provide it. The result of the cost sheet is shown here.
Note on M39: martin kramer: This is the calculated business value. It is only relevant in comparison with other projects

## Cost
Project Initiation Survey
Cost Driver (all in k€)
Instruction | Fill out the green fields, use the space below for further side calculations, if needed; adjust the contingency and provide a comment for that if required
| IT | Function
Project Total | 0 | 0 | Standard Contingency: | 20%
IT Project Cost | Cost Type | Cost (in 1.000€) | Comments
Software
Hardware
Internal Resources
External Resources
External Suppliers
Training
Travel
Others
Operating Cost
| Contingency | 0
| Total | 0
Function Project Cost | Cost Type | Cost (in 1.000€) | Comments
Internal Resources
Consulting
Supplier Implementation
Supplier Change Requests
Training
Travel
Others
| Contingency | 0
| Total | 0
General Cost Comment
No detailed cost estimation available, yet

## Admin
Nr | Question | Weight | Comment | 1 - Very little | 2 - Little | 3 - Medium | 4 - High | 5 - Very High
1 | Does it support the data integrity initiative? | 3 | System / tool is not sufficient, but could support / enable data integrity | 1 - data integrity not effected | 2 - little improvement | 3 - medium improvement | 4 - high improvement | 5 - very high improvement
2 | Does it increase efficiency / lower cost? | 5 |  | 1 - no cost savings | 2 - little improvement or small cost savings | 3 - cost savings between 50k€ and 250k€ (overall) | 4 - cost savings between 250k€ and 1m€ (overall) | 5 - cost savings more than 1m€ (overall)
3 | What it the number of effected employees? | 3 |  | 1 - very few employees effected | 2 - less than 100 employees effected | 3 - between 100 and 5.000 employees effected | 4 - more than 5.000 employees effected | 5 - potentially all employees effected
4 | In how far does it improve system integration? | 3 | System integration | 1 - no impact on system integration | 2 - little impact on system integration | 3 - some improvement in system integration (e.g. new automatic interface) | 4 - process well integrated | 5 - process seamlessly integrated over different systems
5 | Does it deliver value (e.g. funcationally improve business processes)? | 7 | Deliver Value | 1 - no added value | 2 - little added value | 3 - medium value, e.g. process considerably improved | 4 - high improvement, e.g. new process implemented | 5 - very high improvement, e.g. new capability implemented
6 | Is it required for governance or to "keep the lights on"? | 10 | some projects do not deliver value, but assure that a current status quo can be kept, these are the things that just have to be done otherwise the "lights will go out". Some other projects are required for legal matters or governance. Here we need to "boost" their value because they will usually only score here and not in any other section | 1 - not applicable | 2 - little impact | 3 - medium impact, e.g. CASRA map assigned | 4 - Currently no further support, current capability at severe risk | 5 - legally required with penalty / loss of service
Strategic Alignment
Mobility Solutions
Local Roots
Flawless Execution
Great Talent Globally
Risk Management
Social Responsibility
Financial Discipline
Lever
Safety
Quality
Productivity
Human Development
Cost
Cost Class
1 - minor cost < 25k€
2 - low cost 25k€ - 75k€
3 - medium cost 75k€ - 150k€
4 - high cost 150k€ - 300k€
5 - very high cost > 300k€
Supported Program Priority
DELIVER: Hire promote & develop the best Talent
DELIVER: Implement an effective OnBoarding practice
Deploy our Cultural Transformation Strategy (alignment/ Engagement/ Enablement)
IMPROVE BY STANDARDIZING: Support the planning initiative and define the competencies of the future
Invest into the future: Make our organization an attractive employer and deploy key talent management initiatives
SAVE: Increase efficiency/meet cost reduction target/ new budget
SAVE: implement cost savind initatives
n/a
Customer Value
Expertise & Partnership
Governance and Compliance
Strategy, Architecture & Integration
Process Simplification & Efficiency
n/a
CoE Initiative
PROCESSES: Improve effectiveness of the deparment's delivery model
ROCESSES: Improve effectiveness of CoE requirements
TALENT SOLUTIONS: Developing Competences
TALENT SOLUTIONS: Optimize talent allocation
TALENT SOLUTIONS: Highly effective employees driving their performance, development, career
TALENT SOLUTIONS: Engaged employees & leaders in right job at right time
TOTAL REWARD: Making the value proposition clear to attract & retain talent, optimizing cost & competitiveness
Talent Acquisition: Build flexible capacity and efficient delivery end to end
TALENT ACQUISITION: Moving towards future practices
TALENT ACQUISITION: Build flexible capacity and efficient delivery end to end
n/a